## Sheet1
Week no. | To Do | Owned By | Deadline | Status | Comments
Week # - Testing Paper Prototypes | Test the Paper Prototype 1 and 2 to new target users | Rhyss and Ranz | 2019-09-15 |  | Done
| Reiterate the Paper Prototype 1 | Rhyss | 2019-09-15 |  | Done
| Reiterate the Paper Prototype 2 | Ranz | 2019-09-15 |  | Done
| Revise Needfinding | Ranz | 2019-09-15 |  | Done
Week # - Developing Digital Mock-up | Create Digital Mock-up for Paper Prototype 1 and 2 | Rhyss and Ranz | 2019-09-15 |  | Done
| Test the Digital Mock-up 1 and 2 to new target users | Rhyss and Ranz | 2019-09-15 |  | Done
| Reiterate the Digital Mock-up 1 | Rhyss | 2019-09-15 |  | Done
| Reiterate the Digital Mock-up 2 | Ranz | 2019-09-15 |  | Done
| Make Powerpoint Presentaion | Rhyss | 2019-09-15 |  | Done